## Overview
Couchbase Production Launch - Readiness Checklist
Project | FIS Multi-Bank Financial Data Platform
Environment | Production (Silent Launch)
Cluster Name | PRODCCDM001
Created Date | 2026-02-12
Overall Progress Summary
Category | Total Items | Completed | Pending | N/A | % Complete | Status
1. Infrastructure & Cluster | 25 | 0 | 25 | 0 | 0% | Not Started
2. Access & Security | 18 | 0 | 18 | 0 | 0% | Not Started
3. Data & Code Deployment | 16 | 0 | 16 | 0 | 0% | Not Started
4. Performance Monitoring | 28 | 0 | 28 | 0 | 0% | Not Started
5. Alerts & Notifications | 15 | 0 | 15 | 0 | 0% | Not Started
6. Backup & Recovery | 12 | 0 | 12 | 0 | 0% | Not Started
7. Operations | 15 | 0 | 15 | 0 | 0% | Not Started
8. Application Integration | 14 | 0 | 14 | 0 | 0% | Not Started
9. Documentation | 12 | 0 | 12 | 0 | 0% | Not Started
10. Go-Live Coordination | 18 | 0 | 18 | 0 | 0% | Not Started
11. Bug Fix Process | 8 | 0 | 8 | 0 | 0% | Not Started
12. Cost & Capacity | 8 | 0 | 8 | 0 | 0% | Not Started
13. Compliance & Audit | 6 | 0 | 6 | 0 | 0% | Not Started
14. Support & Escalation | 6 | 0 | 6 | 0 | 0% | Not Started
TOTAL | 201 | 0 | 201 | 0 | 0% | Not Started

## 1. Infrastructure
Infrastructure & Cluster Configuration
# | Category | Checklist Item | Status | Owner | Target Date | Completion Date | Notes | Priority
1 | Cluster Sizing & Resources
2 |  | Production cluster matches approved configuration: 5 Data (32vCPU/64GB/P30), 2 Index (32vCPU/64GB/P15), 2 Query (16vCPU/64GB/P6), 3 Eventing (32vCPU/64GB/P10) | Pending |  |  |  |  | Critical
3 |  | Landing bucket: 4GB memory quota, 2 replicas | Pending |  |  |  |  | Critical
4 |  | Process bucket: 4GB memory quota, 2 replicas | Pending |  |  |  |  | Critical
5 |  | Semantic bucket: 14GB memory quota, 2 replicas | Pending |  |  |  |  | Critical
6 |  | Bucket eviction policy set to Value eviction | Pending |  |  |  |  | Medium
7 |  | Total storage capacity validated: ~3.2TB usable | Pending |  |  |  |  | High
8 |  | Auto-compaction settings configured (30% fragmentation, 2-6 AM window) | Pending |  |  |  |  | High
9 |  | Index storage mode: Plasma (default) | Pending |  |  |  |  | Medium
10 |  | Production VNet/subnet properly configured | Pending |  |  |  |  | Critical
11 |  | NSG rules allow Couchbase ports (8091-8096, 9100-9105, 11210, 18091-18096) | Pending |  |  |  |  | Critical
12 |  | DNS resolution working for all cluster nodes | Pending |  |  |  |  | Critical
13 | High Availability & DR
14 |  | XDCR replication configured: Central US → East US 2 | Pending |  |  |  |  | Critical
15 |  | XDCR compression enabled | Pending |  |  |  |  | High
16 |  | XDCR replication validated: lag <2s, zero errors | Pending |  |  |  |  | Critical
17 |  | DR cluster mirrors production configuration | Pending |  |  |  |  | Critical
18 |  | Failover procedures documented | Pending |  |  |  |  | Critical
19 |  | RTO/RPO targets documented: RTO <15min, RPO <2s | Pending |  |  |  |  | Critical
20 |  | Auto-failover enabled: 120s timeout, max 3 failovers | Pending |  |  |  |  | Critical
21 |  | Data service failover enabled | Pending |  |  |  |  | Critical
22 | Network Configuration
23 |  | Private Link/Service Endpoint configured (if applicable) | Pending |  |  |  |  | Medium
24 |  | Load balancer health checks configured | Pending |  |  |  |  | High
25 |  | Network latency between regions tested (<50ms) | Pending |  |  |  |  | High
26 |  | Bandwidth capacity validated for EOD burst (310K txns) | Pending |  |  |  |  | High
27 |  | Azure ExpressRoute/VPN configured (if required) | Pending |  |  |  |  | Low
28 |  | Firewall rules documented | Pending |  |  |  |  | Medium

## 2. Access & Security
Access Management & Security
# | Category | Checklist Item | Status | Owner | Target Date | Completion Date | Notes | Priority
1 | User Access & RBAC
2 |  | Cluster Admin account created (emergency only) | Pending |  |  |  |  | Critical
3 |  | Bucket Admin accounts per application team | Pending |  |  |  |  | High
4 |  | Read-only monitoring accounts created | Pending |  |  |  |  | High
5 |  | Application service accounts created | Pending |  |  |  |  | Critical
6 |  | RBAC roles properly assigned per principle of least privilege | Pending |  |  |  |  | Critical
7 |  | Password policy enforced: min 12 chars, complexity enabled | Pending |  |  |  |  | High
8 |  | Password rotation schedule: 90 days | Pending |  |  |  |  | Medium
9 |  | No default credentials in use (Administrator/password) | Pending |  |  |  |  | Critical
10 |  | Service account credentials stored in Azure Key Vault | Pending |  |  |  |  | Critical
11 |  | Credential rotation procedure documented | Pending |  |  |  |  | High
12 | Network Security
13 |  | Allowed IP addresses configured (application servers only) | Pending |  |  |  |  | Critical
14 |  | Jump box/bastion host access configured | Pending |  |  |  |  | High
15 |  | NO 0.0.0.0/0 (open to world) in allowed IPs | Pending |  |  |  |  | Critical
16 |  | Client-to-cluster TLS encryption enabled | Pending |  |  |  |  | Critical
17 |  | Node-to-node encryption enabled | Pending |  |  |  |  | High
18 |  | Valid SSL certificates installed | Pending |  |  |  |  | Critical
19 |  | Certificate expiry monitoring configured (30-day alert) | Pending |  |  |  |  | High
20 | Audit & Compliance
21 |  | Audit logging enabled for admin actions | Pending |  |  |  |  | Critical
22 |  | Data access logging enabled (if required) | Pending |  |  |  |  | Medium
23 |  | Logs forwarded to SIEM/log aggregation | Pending |  |  |  |  | High
24 |  | Log retention policy: 90 days minimum | Pending |  |  |  |  | High
25 |  | Encryption at rest enabled (Azure disk encryption) | Pending |  |  |  |  | Critical
26 |  | Encryption in transit (TLS) | Pending |  |  |  |  | Critical
27 |  | Key management via Azure Key Vault | Pending |  |  |  |  | Critical
28 |  | PII/PHI fields identified and documented | Pending |  |  |  |  | High

## 3. Data & Code Deploy
Data & Code Deployment
# | Category | Checklist Item | Status | Owner | Target Date | Completion Date | Notes | Priority
1 | Bucket & Schema
2 |  | All buckets created with correct memory quotas | Pending |  |  |  |  | Critical
3 |  | Replica count: 2 for all buckets | Pending |  |  |  |  | Critical
4 |  | Durability requirements defined | Pending |  |  |  |  | High
5 |  | Compression enabled (SNAPPY) | Pending |  |  |  |  | Medium
6 |  | All required secondary indexes created | Pending |  |  |  |  | Critical
7 |  | Index definitions match UAT | Pending |  |  |  |  | Critical
8 |  | All indexes built successfully (0 items remaining) | Pending |  |  |  |  | Critical
9 |  | Index replica enabled | Pending |  |  |  |  | High
10 | Eventing Functions
11 |  | All 5+ eventing functions exported from UAT | Pending |  |  |  |  | Critical
12 |  | Bucket bindings updated for production bucket names | Pending |  |  |  |  | Critical
13 |  | External URLs updated to production endpoints | Pending |  |  |  |  | Critical
14 |  | Functions deployed successfully | Pending |  |  |  |  | Critical
15 |  | Functions processing events (DCP backlog draining) | Pending |  |  |  |  | Critical
16 | Initial Data Migration
17 |  | Data loaded via bulk import (if applicable) | Pending |  |  |  |  | High
18 |  | Document count verified | Pending |  |  |  |  | High
19 |  | Data integrity checks passed | Pending |  |  |  |  | Critical
20 |  | Working set fits in memory quota (resident ratio >90%) | Pending |  |  |  |  | High
21 | Application Code
22 |  | Connection strings point to production cluster | Pending |  |  |  |  | Critical
23 |  | Credentials use Azure Key Vault (no hardcoded) | Pending |  |  |  |  | Critical
24 |  | Retry logic and circuit breakers configured | Pending |  |  |  |  | High
25 |  | Timeout settings appropriate (2.5s query, 10s KV) | Pending |  |  |  |  | Medium
26 |  | Latest stable Couchbase SDK version | Pending |  |  |  |  | High
27 |  | Connection pooling configured (min 5, max 50) | Pending |  |  |  |  | High
28 | Kafka Integration
29 |  | Kafka Connect to Couchbase validated | Pending |  |  |  |  | Critical
30 |  | Source topics mapped correctly | Pending |  |  |  |  | Critical
31 |  | Target buckets correct (landing → process → semantic) | Pending |  |  |  |  | Critical
32 |  | Error handling configured | Pending |  |  |  |  | High
33 |  | Dead letter queue configured | Pending |  |  |  |  | High

## 4. Performance Monitoring
Performance Monitoring
# | Category | Checklist Item | Status | Owner | Target Date | Completion Date | Notes | Priority
1 | Monitoring Tools Setup
2 |  | Couchbase UI monitoring access for on-call team | Pending |  |  |  |  | High
3 |  | Key metrics dashboards created | Pending |  |  |  |  | High
4 |  | Historical data retention: 90 days | Pending |  |  |  |  | Medium
5 |  | Azure Monitor integration configured | Pending |  |  |  |  | High
6 |  | Custom dashboards created in Azure | Pending |  |  |  |  | Medium
7 |  | Log Analytics workspace configured | Pending |  |  |  |  | High
8 |  | APM integration (New Relic/Datadog/AppInsights) | Pending |  |  |  |  | High
9 |  | Couchbase operations tracked in APM | Pending |  |  |  |  | Medium
10 |  | Slow query logging enabled (>5s) | Pending |  |  |  |  | High
11 | Data Service Metrics
12 |  | mem_used / mem_total monitoring (alert >80%) | Pending |  |  |  |  | Critical
13 |  | vb_active_resident_items_ratio (alert <90%) | Pending |  |  |  |  | Critical
14 |  | cmd_get, cmd_set rates tracked | Pending |  |  |  |  | High
15 |  | ep_cache_miss_rate monitoring (alert >5%) | Pending |  |  |  |  | High
16 |  | Disk queue depth monitoring | Pending |  |  |  |  | High
17 |  | OOM error monitoring (should be 0) | Pending |  |  |  |  | Critical
18 | Index Service Metrics
19 |  | Index memory usage monitoring (alert >80%) | Pending |  |  |  |  | High
20 |  | Index scan rate tracked | Pending |  |  |  |  | Medium
21 |  | Index build time monitoring | Pending |  |  |  |  | Medium
22 |  | Index fragmentation monitoring (alert >30%) | Pending |  |  |  |  | High
23 |  | Index disk usage tracking | Pending |  |  |  |  | Medium
24 | Query Service Metrics
25 |  | Query requests/sec tracked | Pending |  |  |  |  | High
26 |  | Query latency p50, p95, p99 monitored | Pending |  |  |  |  | Critical
27 |  | Prepared statement count tracked | Pending |  |  |  |  | Low
28 |  | Active requests monitoring | Pending |  |  |  |  | Medium
29 |  | Query errors/timeouts (alert >1%) | Pending |  |  |  |  | Critical
30 | Eventing Service Metrics
31 |  | DCP backlog monitoring (alert >10K) | Pending |  |  |  |  | High
32 |  | Execution success/failure count tracked | Pending |  |  |  |  | Critical
33 |  | Timeout count monitoring (should be 0) | Pending |  |  |  |  | Critical
34 |  | Worker utilization tracked | Pending |  |  |  |  | Medium
35 |  | Function deployment status monitoring | Pending |  |  |  |  | High
36 | XDCR Metrics
37 |  | Replication lag monitoring (alert >2s) | Pending |  |  |  |  | Critical
38 |  | Changes queue size tracked | Pending |  |  |  |  | High
39 |  | Replication errors (alert >0) | Pending |  |  |  |  | Critical
40 |  | Bandwidth utilization monitored | Pending |  |  |  |  | Medium
41 |  | Docs processed/sec tracked | Pending |  |  |  |  | Medium
42 | Performance Baselines
43 |  | UAT baseline metrics documented | Pending |  |  |  |  | High
44 |  | Average mutation rate: 500/min baseline | Pending |  |  |  |  | Medium
45 |  | Average query rate: 800/min baseline | Pending |  |  |  |  | Medium
46 |  | EOD burst capacity validated: 310K txns | Pending |  |  |  |  | Critical
47 |  | Performance targets defined (p95 <100ms queries) | Pending |  |  |  |  | High

## 5. Alerts & Notifications
Alerts & Notifications
# | Category | Checklist Item | Status | Owner | Target Date | Completion Date | Notes | Priority
1 | Critical Alerts (Immediate)
2 |  | Node failure detection alert | Pending |  |  |  |  | Critical
3 |  | Auto-failover triggered alert | Pending |  |  |  |  | Critical
4 |  | Disk full >85% alert | Pending |  |  |  |  | Critical
5 |  | Memory usage >90% alert | Pending |  |  |  |  | Critical
6 |  | Rebalance failed alert | Pending |  |  |  |  | Critical
7 |  | XDCR replication stopped alert | Pending |  |  |  |  | Critical
8 |  | XDCR lag >10s alert | Pending |  |  |  |  | Critical
9 |  | Eventing function failure rate >1% alert | Pending |  |  |  |  | Critical
10 |  | OOM errors alert | Pending |  |  |  |  | Critical
11 | Warning Alerts (1 hour)
12 |  | Disk usage >75% warning | Pending |  |  |  |  | High
13 |  | Memory usage >80% warning | Pending |  |  |  |  | High
14 |  | Index fragmentation >30% warning | Pending |  |  |  |  | Medium
15 |  | Query latency p95 >200ms warning | Pending |  |  |  |  | High
16 |  | Eventing backlog >10K items warning | Pending |  |  |  |  | High
17 |  | Slow queries >5s warning | Pending |  |  |  |  | Medium
18 | Info Alerts
19 |  | Scheduled rebalance notifications | Pending |  |  |  |  | Low
20 |  | Index build triggered notifications | Pending |  |  |  |  | Low
21 |  | Compaction started/completed notifications | Pending |  |  |  |  | Low
22 | Alert Channels
23 |  | PagerDuty/OpsGenie integration for critical alerts | Pending |  |  |  |  | Critical
24 |  | Slack/Teams #couchbase-prod-alerts channel | Pending |  |  |  |  | High
25 |  | Email DL for production support team | Pending |  |  |  |  | High
26 |  | Runbook links included in alert messages | Pending |  |  |  |  | High

## 6. Backup & Recovery
Backup & Recovery
# | Category | Checklist Item | Status | Owner | Target Date | Completion Date | Notes | Priority
1 | Backup Strategy
2 |  | Full backup scheduled: Weekly (Sunday 2 AM) | Pending |  |  |  |  | Critical
3 |  | Incremental backup scheduled: Daily (2 AM) | Pending |  |  |  |  | Critical
4 |  | Backup retention policy: 30 days | Pending |  |  |  |  | High
5 |  | Backup location: Azure Blob Storage (GRS) | Pending |  |  |  |  | Critical
6 |  | Test restore performed successfully | Pending |  |  |  |  | Critical
7 |  | Restore time documented (meets RTO) | Pending |  |  |  |  | High
8 |  | Restore procedure documented | Pending |  |  |  |  | High
9 |  | Backup integrity checks automated | Pending |  |  |  |  | High
10 | Backup Tools
11 |  | cbbackupmgr configured and tested | Pending |  |  |  |  | Critical
12 |  | Backup repository created | Pending |  |  |  |  | Critical
13 |  | Backup credentials in Key Vault | Pending |  |  |  |  | High
14 |  | Backup logs monitored | Pending |  |  |  |  | Medium
15 | Recovery Procedures
16 |  | DR failover runbook created | Pending |  |  |  |  | Critical
17 |  | Rollback procedure documented | Pending |  |  |  |  | Critical
18 |  | Contact list for escalation | Pending |  |  |  |  | High
19 |  | Expected RTO documented: 15 minutes | Pending |  |  |  |  | High
20 |  | Expected RPO documented: <2 seconds | Pending |  |  |  |  | High
21 |  | Point-in-time recovery procedure documented | Pending |  |  |  |  | High
22 |  | Data validation steps defined | Pending |  |  |  |  | High
23 |  | Application cutover process documented | Pending |  |  |  |  | High

## 7. Operations
Operational Procedures
# | Category | Checklist Item | Status | Owner | Target Date | Completion Date | Notes | Priority
1 | Change Management
2 |  | Deployment process documented | Pending |  |  |  |  | High
3 |  | Blue-green deployment strategy for eventing | Pending |  |  |  |  | High
4 |  | Rollback procedure documented | Pending |  |  |  |  | Critical
5 |  | Deployment windows defined (off-peak only) | Pending |  |  |  |  | High
6 |  | CAB approval process for prod changes | Pending |  |  |  |  | High
7 |  | Code review process for eventing functions | Pending |  |  |  |  | High
8 |  | Index change review process | Pending |  |  |  |  | Medium
9 |  | Load testing requirement in UAT | Pending |  |  |  |  | High
10 | Maintenance Procedures
11 |  | Rebalance procedures documented | Pending |  |  |  |  | High
12 |  | Rebalance monitoring process defined | Pending |  |  |  |  | Medium
13 |  | Upgrade procedures documented | Pending |  |  |  |  | High
14 |  | Rolling upgrade procedure tested | Pending |  |  |  |  | Medium
15 |  | Auto-compaction configured (30% frag, 2-6 AM) | Pending |  |  |  |  | High
16 |  | Manual compaction procedure documented | Pending |  |  |  |  | Low
17 | Troubleshooting
18 |  | Node failure recovery runbook | Pending |  |  |  |  | Critical
19 |  | Replication lag resolution runbook | Pending |  |  |  |  | High
20 |  | OOM troubleshooting runbook | Pending |  |  |  |  | High
21 |  | Slow query analysis runbook | Pending |  |  |  |  | Medium
22 |  | cbcollect_info usage documented | Pending |  |  |  |  | Medium
23 |  | Log locations documented | Pending |  |  |  |  | Medium
24 |  | Support ticket process documented | Pending |  |  |  |  | High
25 |  | Escalation path to Couchbase Support | Pending |  |  |  |  | High

## 8. App Integration
Application Integration
# | Category | Checklist Item | Status | Owner | Target Date | Completion Date | Notes | Priority
1 | Connection Management
2 |  | Connection pool min: 5, max: 50 | Pending |  |  |  |  | High
3 |  | Connection timeout: 10s | Pending |  |  |  |  | Medium
4 |  | Idle timeout: 180s | Pending |  |  |  |  | Low
5 |  | Exponential backoff for retries | Pending |  |  |  |  | High
6 |  | Max retry attempts: 3 | Pending |  |  |  |  | Medium
7 |  | Circuit breaker configured | Pending |  |  |  |  | High
8 |  | Client-side load balancing enabled | Pending |  |  |  |  | High
9 |  | Node failure detection <10s | Pending |  |  |  |  | Medium
10 | Query Optimization
11 |  | All queries use prepared statements | Pending |  |  |  |  | Critical
12 |  | Covering indexes for frequent queries | Pending |  |  |  |  | High
13 |  | Appropriate use of projections (SELECT specific fields) | Pending |  |  |  |  | Medium
14 |  | Pagination for large result sets | Pending |  |  |  |  | High
15 | Testing
16 |  | Load testing: EOD burst (310K txns) validated | Pending |  |  |  |  | Critical
17 |  | Load testing: Morning retail (10K txns) validated | Pending |  |  |  |  | High
18 |  | Average load validated: 500 mutations/min, 800 queries/min | Pending |  |  |  |  | High
19 |  | Node failure simulated and validated | Pending |  |  |  |  | Critical
20 |  | Auto-failover validated | Pending |  |  |  |  | Critical
21 |  | DR regional failover tested | Pending |  |  |  |  | Critical
22 |  | RTO <15min achieved in test | Pending |  |  |  |  | Critical
23 |  | RPO <2s achieved in test | Pending |  |  |  |  | Critical

## 9. Documentation
Documentation
# | Category | Checklist Item | Status | Owner | Target Date | Completion Date | Notes | Priority
1 | Architecture Documentation
2 |  | Cluster architecture diagram (node topology) | Pending |  |  |  |  | High
3 |  | Service distribution diagram | Pending |  |  |  |  | High
4 |  | Network diagram | Pending |  |  |  |  | High
5 |  | XDCR topology diagram | Pending |  |  |  |  | High
6 |  | Data flow diagram (FIS→Kafka→Couchbase) | Pending |  |  |  |  | High
7 |  | Eventing function flow diagram | Pending |  |  |  |  | Medium
8 | Operational Documentation
9 |  | Deployment runbook | Pending |  |  |  |  | Critical
10 |  | Failover runbook | Pending |  |  |  |  | Critical
11 |  | Backup/restore runbook | Pending |  |  |  |  | Critical
12 |  | Troubleshooting guides | Pending |  |  |  |  | High
13 |  | Cluster configuration documentation | Pending |  |  |  |  | High
14 |  | Bucket settings documentation | Pending |  |  |  |  | Medium
15 |  | Index definitions documentation | Pending |  |  |  |  | Medium
16 |  | Eventing function code documentation | Pending |  |  |  |  | Medium
17 | Access Documentation
18 |  | RBAC matrix documented | Pending |  |  |  |  | High
19 |  | Service account inventory | Pending |  |  |  |  | High
20 |  | Key Vault secrets inventory | Pending |  |  |  |  | High
21 | Knowledge Transfer
22 |  | Operations team trained on Couchbase | Pending |  |  |  |  | Critical
23 |  | On-call team has runbook access | Pending |  |  |  |  | Critical
24 |  | Escalation procedures communicated | Pending |  |  |  |  | High

## 10. Go-Live
Go-Live Coordination
# | Category | Checklist Item | Status | Owner | Target Date | Completion Date | Notes | Priority
1 | Pre-Launch Validation
2 |  | Write test document → verify in all 3 buckets | Pending |  |  |  |  | Critical
3 |  | Query test → verify results | Pending |  |  |  |  | Critical
4 |  | Eventing function test → verify processing | Pending |  |  |  |  | Critical
5 |  | XDCR replication test → verify DR cluster | Pending |  |  |  |  | Critical
6 |  | 5% traffic routing configured | Pending |  |  |  |  | Critical
7 |  | Monitoring dashboards active and validated | Pending |  |  |  |  | Critical
8 |  | On-call team ready and briefed | Pending |  |  |  |  | Critical
9 |  | Rollback procedure ready | Pending |  |  |  |  | Critical
10 | Launch Timeline
11 |  | T-24h: Final UAT validation completed | Pending |  |  |  |  | Critical
12 |  | T-12h: Configuration freeze in effect | Pending |  |  |  |  | Critical
13 |  | T-2h: All monitoring active | Pending |  |  |  |  | Critical
14 |  | T-1h: On-call team briefed | Pending |  |  |  |  | Critical
15 |  | T-0: Traffic cutover begins (5%) | Pending |  |  |  |  | Critical
16 |  | T+1h: Monitor, increase to 25% | Pending |  |  |  |  | Critical
17 |  | T+4h: Monitor, increase to 50% | Pending |  |  |  |  | Critical
18 |  | T+8h: Monitor, increase to 100% | Pending |  |  |  |  | Critical
19 | Rollback Criteria
20 |  | Rollback if error rate >1% | Pending |  |  |  |  | Critical
21 |  | Rollback if latency p95 >500ms | Pending |  |  |  |  | Critical
22 |  | Rollback if data loss detected | Pending |  |  |  |  | Critical
23 |  | Rollback if XDCR replication failure | Pending |  |  |  |  | Critical
24 | Post-Launch
25 |  | Day 1 review: performance vs baseline | Pending |  |  |  |  | High
26 |  | Day 1 review: alerts analysis | Pending |  |  |  |  | High
27 |  | Week 1 review: capacity planning | Pending |  |  |  |  | Medium
28 |  | Week 1 review: documentation updates | Pending |  |  |  |  | Low

## 11. Bug Fix Process
Bug Fixes & Hotfix Process
# | Category | Checklist Item | Status | Owner | Target Date | Completion Date | Notes | Priority
1 | Severity Classification
2 |  | P0 (Critical): Data loss, cluster down - Response: Immediate, Fix: <2h | Pending |  |  |  |  | Critical
3 |  | P1 (High): Performance degradation - Response: <1h, Fix: <24h | Pending |  |  |  |  | High
4 |  | P2 (Medium): Minor functionality - Response: <4h, Fix: <1 week | Pending |  |  |  |  | Medium
5 |  | P3 (Low): Cosmetic - Response: Next sprint | Pending |  |  |  |  | Low
6 | Hotfix Process
7 |  | Hotfix deployment procedure documented | Pending |  |  |  |  | Critical
8 |  | CAB approval process for P0/P1 hotfixes | Pending |  |  |  |  | High
9 |  | Test in DR before primary deployment | Pending |  |  |  |  | Critical
10 |  | Post-mortem template available | Pending |  |  |  |  | Medium
11 | Component-Specific Hotfix
12 |  | Eventing function hotfix procedure documented | Pending |  |  |  |  | High
13 |  | Index hotfix procedure (online rebuild) | Pending |  |  |  |  | Medium
14 |  | Query optimization hotfix procedure | Pending |  |  |  |  | Low
15 |  | Configuration hotfix procedure | Pending |  |  |  |  | Medium

## 12. Cost & Capacity
Cost Optimization & Capacity Planning
# | Category | Checklist Item | Status | Owner | Target Date | Completion Date | Notes | Priority
1 | Cost Monitoring
2 |  | Azure cost tags applied (Environment, Project, Cost Center) | Pending |  |  |  |  | High
3 |  | Monthly cost review process established | Pending |  |  |  |  | Medium
4 |  | Compute costs tracked | Pending |  |  |  |  | Medium
5 |  | Storage costs tracked (disk + backup) | Pending |  |  |  |  | Medium
6 |  | Network egress costs tracked | Pending |  |  |  |  | Low
7 | Capacity Planning
8 |  | Data growth projections documented | Pending |  |  |  |  | High
9 |  | Transaction growth projections documented | Pending |  |  |  |  | High
10 |  | Capacity thresholds defined | Pending |  |  |  |  | High
11 | Scaling Triggers
12 |  | Disk >70% → Add storage or compact | Pending |  |  |  |  | High
13 |  | Memory >80% sustained → Increase memory | Pending |  |  |  |  | High
14 |  | CPU >80% sustained → Add nodes or scale up | Pending |  |  |  |  | High
15 |  | Index build time >4h → Add index nodes | Pending |  |  |  |  | Medium

## 13. Compliance
Compliance & Audit
# | Category | Checklist Item | Status | Owner | Target Date | Completion Date | Notes | Priority
1 | Audit Trail
2 |  | Change log maintained for all prod changes | Pending |  |  |  |  | High
3 |  | Configuration changes logged | Pending |  |  |  |  | High
4 |  | Access changes logged | Pending |  |  |  |  | High
5 |  | Automated via Couchbase audit log | Pending |  |  |  |  | High
6 | Compliance Reports
7 |  | Access review: Monthly | Pending |  |  |  |  | High
8 |  | Security scan: Quarterly | Pending |  |  |  |  | Medium
9 |  | DR test: Quarterly | Pending |  |  |  |  | Critical
10 |  | Backup validation: Monthly | Pending |  |  |  |  | High

## 14. Support
Support & Escalation
# | Category | Checklist Item | Status | Owner | Target Date | Completion Date | Notes | Priority
1 | Support Contacts
2 |  | L1: Application support team contacts documented | Pending |  |  |  |  | High
3 |  | L2: Platform/DevOps team contacts documented | Pending |  |  |  |  | High
4 |  | L3: Couchbase SME contacts documented | Pending |  |  |  |  | High
5 |  | Couchbase Support portal access confirmed | Pending |  |  |  |  | High
6 |  | Support contract priority level documented | Pending |  |  |  |  | Medium
7 |  | Escalation path to Couchbase TAM documented | Pending |  |  |  |  | Medium
8 | Incident Management
9 |  | Incident severity definitions documented | Pending |  |  |  |  | High
10 |  | Response SLAs documented | Pending |  |  |  |  | High
11 |  | Communication plan documented | Pending |  |  |  |  | High
12 |  | Post-mortem template available | Pending |  |  |  |  | Medium