## Staggered Renewal Model
Enterprise Plan - Staggered 24-Month Credit Renewal Plan (Aug 2026 - Jul 2028)
PRDCCDMAZCEN_001 (Central US) + PRDCCDMAZEST2_001 (East US 2)
Assumptions
PRDCCDMAZCEN_001 - full capacity credits/mo (14 nodes: 5 Data/3 Index/3 Query/3 Eventing) |  |  | 22849.26
PRDCCDMAZCEN_001 - downsized credits/mo (13 nodes: 3 Data/3 Index/5 Query/2 Eventing, per Capella) |  |  | 15902.04
PRDCCDMAZEST2_001 - credits/mo (held at full capacity throughout) |  |  | 12700
Buffer % applied to final procurement total |  |  | 10%
Downsize figure taken directly from the Capella node config screen for the target service group layout (Data 3 / Index 3 / Query 5 / Eventing 2). East US 2 is not being downsized this cycle.
Phase Plan
Phase | Description | Months | Duration | CEN % of Full | EST2 % of Full
P1 | Baseline monitoring at current capacity | Aug-Oct 2026 | 3 mo | 100% | 100%
P2 | Downsize Central per Capella config; East 2 unchanged | Nov 2026-Apr 2027 | 6 mo | see below | 100%
P3 | Conditional upscale, need-basis (placeholder avg) | May-Oct 2027 | 6 mo | see below | 100%
P4 | Full capacity - ramp complete, steady state to term end | Nov 2027-Jul 2028 | 9 mo | 100% | 100%
PRDCCDMAZCEN_001 credits/mo by phase
Phase | Credits/mo (CEN) | % of Full
P1 | 22849.26 | 100%
P2 | 15902.04 | 69.6%
P3 | 18186.966 | 79.6%
P4 | 22849.26 | 100%
P3 is a planning placeholder only (downsized level + 10% of full) - true up monthly once actual utilization during P1/P2 is known.
24-Month Monthly Projection
# | Month | Phase | PRDCCDMAZCEN_001 | PRDCCDMAZEST2_001 | Total Credits/mo | Cumulative Credits
1 | Aug-2026 | P1 | 22849.26 | 12700 | 35549.26 | 35549.26
2 | Sep-2026 | P1 | 22849.26 | 12700 | 35549.26 | 71098.52
3 | Oct-2026 | P1 | 22849.26 | 12700 | 35549.26 | 106647.78
4 | Nov-2026 | P2 | 15902.04 | 12700 | 28602.04 | 135249.82
5 | Dec-2026 | P2 | 15902.04 | 12700 | 28602.04 | 163851.86
6 | Jan-2027 | P2 | 15902.04 | 12700 | 28602.04 | 192453.9
7 | Feb-2027 | P2 | 15902.04 | 12700 | 28602.04 | 221055.94
8 | Mar-2027 | P2 | 15902.04 | 12700 | 28602.04 | 249657.98
9 | Apr-2027 | P2 | 15902.04 | 12700 | 28602.04 | 278260.02
10 | May-2027 | P3 | 18186.966 | 12700 | 30886.966 | 309146.986
11 | Jun-2027 | P3 | 18186.966 | 12700 | 30886.966 | 340033.952
12 | Jul-2027 | P3 | 18186.966 | 12700 | 30886.966 | 370920.918
13 | Aug-2027 | P3 | 18186.966 | 12700 | 30886.966 | 401807.884
14 | Sep-2027 | P3 | 18186.966 | 12700 | 30886.966 | 432694.85
15 | Oct-2027 | P3 | 18186.966 | 12700 | 30886.966 | 463581.816
16 | Nov-2027 | P4 | 22849.26 | 12700 | 35549.26 | 499131.076
17 | Dec-2027 | P4 | 22849.26 | 12700 | 35549.26 | 534680.336
18 | Jan-2028 | P4 | 22849.26 | 12700 | 35549.26 | 570229.596
19 | Feb-2028 | P4 | 22849.26 | 12700 | 35549.26 | 605778.856
20 | Mar-2028 | P4 | 22849.26 | 12700 | 35549.26 | 641328.116
21 | Apr-2028 | P4 | 22849.26 | 12700 | 35549.26 | 676877.376
22 | May-2028 | P4 | 22849.26 | 12700 | 35549.26 | 712426.636
23 | Jun-2028 | P4 | 22849.26 | 12700 | 35549.26 | 747975.896
24 | Jul-2028 | P4 | 22849.26 | 12700 | 35549.26 | 783525.156
Summary - 2-Year Staggered Procurement
Total credits - 24 months, staggered (pre-buffer) |  |  | 783525.156
Buffer applied |  |  | 10%
TOTAL CREDITS TO PROCURE (2 yrs, staggered, with buffer) |  |  | 861877.6716
Comparator - flat full-capacity estimate x24 months (pre-buffer) |  |  | 853182.24
Comparator - flat full-capacity, with buffer (matches original renewal method x2 yrs) |  |  | 938500.464
Estimated credit savings, staggered vs. flat 2-yr estimate |  |  | 76622.7924
Savings as % of flat 2-yr estimate |  |  | 8.164%
Next step: monitor actual utilization monthly through P1-P2, confirm the P3 need-basis level, then lock the final 2-yr purchase quantity with the vendor before renewal.