## Demo Preparation Plan
Step No | Phase | Owner | Detailed Action | Validation Checklist | Risk / Backup Plan | Status (To Fill) | Notes
1 | Architecture Overview | Mahesh | Prepare single architecture slide showing FIS → Confluent → Kafka Connector → Couchbase Landing → Process → Semantic. | Slide reviewed internally; no deep technical overload; clear business value message. | Keep static architecture screenshot ready if screen share fails.
2 | Environment Health Check | All | Validate Confluent cluster, Kafka connectors, Couchbase cluster, Eventing functions, indexes, and private endpoints. | All services green; no rebalancing; no connector lag; no pending firewall changes. | Take screenshots of health dashboards.
3 | Trigger Event Preparation | Test User | Login to test bank and prepare scenario for generating FIS transaction. | Credentials verified; test case pre-filled; internet stable. | Keep previously generated transaction ID ready.
4 | Confluent Topic Validation | Aditya | Open topic UI and filter for transaction ID; monitor offset increment. | Topic visible; partition assigned; offset increases in real-time. | Keep message payload screenshot ready.
5 | Kafka Connector Validation | Aditya | Verify connector status and logs to confirm successful processing. | Connector in RUNNING state; no errors in logs. | Screenshot of successful connector run.
6 | Couchbase Landing Layer | Mahesh | Query landing collection and show raw JSON document for transaction. | Document count increases; filter by transaction ID successful. | Have saved document screenshot ready.
7 | Couchbase Process Layer | Mahesh | Show transformed/enriched document after business logic processing. | Processed collection updated; expected fields present. | Keep sample processed document ready.
8 | Couchbase Semantic Layer | Mahesh | Demonstrate business-ready document and run sample N1QL query. | Query executes quickly; indexed fields working. | Pre-run query and store result screenshot.
9 | DR & Resilience Talking Points | Mahesh | Prepare short explanation on multi-region DR, XDCR, cluster linking, RPO/RTO. | Clear 1-2 line explanation ready. | Keep DR architecture diagram screenshot.
10 | Full Dry Run Rehearsal | All | Execute complete end-to-end rehearsal at least twice. | Measure end-to-end latency; confirm smooth transitions between speakers. | Document fallback order if live demo fails.
11 | Freeze Changes Before Demo | All | Ensure no deployments, scaling, or connector modifications before demo. | Confirm change freeze via team communication. | Notify team if any instability detected.
12 | Meeting Logistics | All | Join 10 minutes early; assign speaking order; test screen share. | Audio, screen share, internet tested. | Keep alternate presenter ready.